## Sheet1
| Number of hours each member | Total number of hours spent (in hours)
Planning and Requirement Analysis
1. Reading and understanding the project | 1 hour * 4 members | 4
2. Research | 2 hours * 4 members | 8
3. Deciding what language | 1 hour * 2 members | 2
4. Deciding what platform to use | 2 hours * 2 members | 4
5. Work plan creation | 3 hours * 4 members | 12
6. Identifying functional requirements | 3 hours * 4 members | 12
7. Non-functional requirements | 3 hours * 4 members | 12
Design
1. Creating Storefront Visual | 2 hours * 2 members | 4
2. App Logo | 2 hours * 1 member | 2
3. Identifying classes | 4 hours * 2 members | 8
4. Identifying the responsibilities of the classes | 2 hours * 4 members | 8
5. Diagrams of class relationships | 2 hours * 4 members | 8
6. Sequence Diagrams | 1 hour * 4 members | 4
7. CRC cards | 1 hour * 4 member | 4
8. Use cases | 1 hour * 4 members | 4
9. Data Collection (what type of structure) | 1 hour * 2 members | 2
Implementation
Coding all classes and methods associated | 5 hours * 3 members | 15
Database creation | 3 hours * 3 members | 9
Testing
1. Creating Accounts, testing interrupts | 2 hours * 4 member | 8
2. Viewing profiles | 2 hours * 4 member | 8
3. Moo-Re Points Algorithm Test | 2 hours * 4 member | 8
4. Writing Review | 2 hours * 4 members | 8
Maintenance
1. Updates (Bugs, new features) | 2 hours * 2 members | 4
Weekly Maintenance | 1 hour * 1 member | 1
COST
Time |  | 167
Labor | 1500 * 4 | 6000
Software Lincesses | 25 | 25
Hardware | $1500 * 4 units | 6000
Others | 1000 | 1000