## Project Plan & Progress
Team: Moo 2 |  | Formatting: | Planned |  | Forecast to miss due date |  |  |  | Forecast to hit due date, currently behind | [5 empty] | Forecast to hit due date, currently on time |  |  |  | Done
Week Ending:
Chapter | Topic | 2016-01-29 | 2016-02-05 | 2016-02-12 | 2016-02-19 | 2016-02-26 | 2016-03-04 | 2016-03-11 | 2016-03-18 | 2016-03-25 | 2016-04-01 | 2016-04-08 | 2016-04-15 | 2016-04-22 | 2016-04-29 | 2016-05-06 | 2016-05-13 | 2016-05-20
High Level Requirements | Description of the Project |  |  |  |  | Planned
| List of high level requirements |  |  |  |  | Planned
| High level requirement descriptions |  |  |  |  | Planned
| User story per each HLR |  |  |  |  | Planned
| Glossary |  |  |  |  | Planned
Requirements Q&A | Q&A From Class |  |  |  |  | Planned
Project Plan & Gantt Chart | Preliminary |  |  |  |  | Planned
Detailed SRS | Number Requirements |  |  |  |  | Planned
| Glossary - classes/methods |  |  |  |  | Planned
| Traceability Matrix - req to user stories |  |  |  |  | Planned
Tyler Olson | Project Manager
Paul Diaz | Programmer
Stefan Francisco | Programmer
Timothy Magallanes | Programmer
Formulas:
Planned = [Formatting:]+7